## Project Profile
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PRJ_BEP_001
Project Name | Bank Exam Portal_01
Prepared/Modified by | Role | Date of Preparation
Mahender Reddy | test engineer | 2018-06-23
Reviewed by | Role | Date of Review
name
Approved by | Role | Date of Approval
Circulation List
Version Number | 1

## Defect Tracking Sheet
Project ID: | PRJ_BEP_001 | Project Name : Bank Exam Portal_01 | [22 empty] | VERIFIED
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments | REOPENED | Coding | Internal Dev
DF_BEP_01 | Bank Exam Portal | The link “List of exams on the portal” is not able to navigate the user to the web page displaying various exams available on the Banking Exam Portal application. | Detailed Description: The List of exams are not available in the Bank Exam Portal, the user web page displays various exams Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Open the Bank exam portal 4. Click the link "List of exams" on the web portal. 5. Username and password should be entered. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the expected link of "list of exams on the portal" is not found. | Design | Internet explorer | Internal Dev | High | Medim | 1.1 | Build 1.0 | 2018-06-25 | Mahender Reddy |  | ACT | Test Cylce 1 | TC_Reg_003
DF_BEP_02 | Bank Exam portal | The link “List of exams on the portal” is displayed at the left side of the web page instead of right side. | Detailed Description: The "List of exams on the portal" is displayed at the left side of the web page instead of right side. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Open Bank Exam Portal Application 4. Click the link "list of exams of the portal" Actual result observed on running above steps: On executing the mentioned steps it is observed that the link "List of exams on the portal" is found to be displayed at the left side of the web page instead of right side. | Code | Internet explorer | Internal dev | Medium | low | 1.1 | Build 1.0 | 2018-06-25 | Mahender Reddy |  | ACT | Test Cylce 1 | TC_Reg_003
DF_BEP_03 | Bank Exam portal | The User Name field is accepting any type of data. | Detailed Descripton: The "List of exams on the portal" is displayed at the user name field is accepting any type of data. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Open Bank Exam Portal Application 4. Click the link "List of Exams on the portal". 5. Enter name in the user name field Actual result observed on running above steps: On executing the above mentioned steps it is observed that in the application the user name field is accepting any type of data. | Code | Internet explorer | Internal Dev | high | high | 1.1 | Build 1.0 | 2018-06-25 | Mahender Reddy |  | ACT | Test Cylce 1 | TC_Reg_003
DF_BEP_04 | Bank Exam portal | The application is not generating an error even if Password filed is left empty while logging to the application | Detailed Descripton: The "List of exams on the portal" is displayed at the user name field is accepting any type of data. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Open Bank Exam Portal Application 4. Click the link "List of Exams on the portal". 5. Enter name in the user name field 6. Password field is left empty. 7. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that in the application password field is left empty while logging to the application without displaying any error message. | Code | Internet explorer | Internal Dev | high | medium | 1.1 | Build 1.0 | 2018-06-25 | Mahender Reddy |  | ACT | Test Cylce 1 | TC_Reg_003
DF_BEP_05 | Bank Exam portal | The application behaves in a wired manner by disallowing a user to login to the website even if the user has entered the valid credential i.e. valid User Name and Password. | Detailed Descripton: The "List of exams on the portal" is displayed at the user name field is accepting any type of data. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Open Bank Exam Portal Application 4. Click the link "List of Exams on the portal". 5. Enter the name in the user name field 6. Enter the password in the password field 7. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the user cannot able to login to the web page even when the valid user name and password is entered. | Code | Internet explorer | Internal Dev | high | high | 1.1 | Build 1.0 | 2018-06-25 | Mahender Reddy |  | ACT | Test Cylce 1 | TC_Reg_003
DF_BEP_06 | Bank Exam portal | After clicking on the Submit button on the home page user gets an error message “Page Cannot Be Displayed”. | Detailed Descripton: The "List of exams on the portal" is displayed at the user name field is accepting any type of data. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Open Bank Exam Portal Application 4. Click the link "List of Exams on the portal". 5. Enter name in the user name field 6. Enter password in the password field 7. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that after clicking on the submit button on the home page user gets an error message "Page Cannot be displayed". | Code |  | Internal Dev | high | high | 1.1 | Build 1.0 | 2018-06-25 | Mahender Reddy |  | ACT | Test Cylce 1 | TC_Reg_003
Note on A3: A unique number for the Defect Id
Note on B3: Give the name of the module being tested
Note on C3: Summarize the defect in 1 or 2 lines
Note on D3: A detailed description of the defect
Note on E3: Categorize the defect into the one of the values given in the drop down list
Note on F3: Mention the name of the browser the defect was found in.
Note on G3: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Enter the Release # in which the defect was detected.
Note on K3: Enter the Build # in which the defect was detected.
Note on L3: Mention the date the defect was reported
Note on M3: Name of the person who reported the defect.
Note on N3: Name of the person the defect is assigned to.
Note on O3: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Mention the Test Case No that the defect was found while testing
Note on R3: Name of the person who fixed the defect.
Note on S3: Mention the date the defect was Fixed
Note on T3: Mention the date the defect was verified
Note on U3: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Enter the Release # in which the defect was available for verification
Note on W3: Enter the Build # in which the defect was available for verification
Note on X3: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.